## Sheet1
User Story # | User Story Name | Tasks | Project Developer | Owner | Acceptance Criteria | Status | Blocked
US1 | Understand Required Dimensions for calls Metrics | Refer Some Dashboards and datalake, list out dimensions | Any BA/Venkat | Nagesh
|  | Peer review with Leads | Any BA/Venkat | Nagesh
|  | Incorporate review comments | Any BA/Venkat | Nagesh
|  | Finalize Dimensions | Any BA/Venkat | Nagesh
|  | Create Query to get data | Any BA/Venkat | Nagesh
US2 | Understand Required Metrics of calls | Refer Some Dashboards and datalake, list out Metrics | Any BA/Venkat | Nagesh
|  | Peer review with Leads | Any BA/Venkat | Nagesh
|  | Incorporate review comments | Any BA/Venkat | Nagesh
|  | Finalize Metrics | Any BA/Venkat | Nagesh
|  | Create Query to get data | Any BA/Venkat | Nagesh
US3 | Understand Required Filters for calls | Refer Some Dashboards and datalake, list out filters | Any BA/Venkat | Nagesh
|  | Peer review with Leads | Any BA/Venkat | Nagesh
|  | Incorporate review comments | Any BA/Venkat | Nagesh
|  | Finalize Filters | Any BA/Venkat | Nagesh
|  | Create Query to get data | Any BA/Venkat | Nagesh
US4 | Create A mongo Collection To store Calls Data | Understand Schema | Venkat | Nagesh
|  | Creat mongo Collection | Venkat | Nagesh
|  | Load Data | Venkat | Nagesh
|  | Peer review with Leads | Venkat | Nagesh
|  | Automate loading process using python | Venkat | Nagesh
US5 | Create A mongo Collection To store Profile Settings | Understand Schema | Venkat | Nagesh
|  | Create mongo Collection | Venkat | Nagesh
|  | Create API using Python for Create/Update/Delete | Venkat | Nagesh
|  | Peer review with Leads | Venkat | Nagesh
|  | Provide Endpoint to UI/UX and Test it | Venkat | Nagesh