## Claims
[7 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11
|  | Project Developer | Owner | Acceptance Criteria | Status | Blocked | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24
User Story | NLP
US0 | Claims Workflow |  | Venkat
US1 | NLP Development - Claim Status | Srilekha | Venkat |  | Done
US2 | NLP Development - Claims (Based on Duration) amount, Adjusted, Billed, Paid, and deined Count etc. | Srilekha | Venkat |  | Done
US3 | Accuracy - Claim Status | Srilekha | Venkat | All the user questions should be answered with 100% Quality. Therte should not be any false response from NLP | Done
US4 | Identify the Month Names, Ranges, Years, Days and Quarters in NLP | Srilekha | Venkat |  | Done
US5 | NLP Development - Average Claim TAT, Biled, Time to resolve (Using Chatito framework or equal framework) | Srilekha | Venkat
US6 | Accuracy - Claims (Based on Duration) amount, Adjusted, Billed, Paid, and deined Count etc. | Srilekha | Venkat | All the user questions should be answered with 100% Quality. Therte should not be any false response from NLP
US7 | Accuracy - Average Claim TAT, Biled, Time to resolve | Srilekha | Venkat
US8 | Integration of intents with MongoDb Queries | Srilekha | Venkat
US9 | Integration of Auto suggestions | Srilekha | Venkat
US10 | Create an training examples for the short questions | Srilekha | Venkat
US11 | Prior Auth Workflow |  | Venkat
US12 | NLP Development - Prior Auth | Vikas | Venkat
US13 | Accuracy - Prior Auth | Vikas | Venkat
US14 | Integration of intents with MongoDb | Vikas | Venkat
US15 | Feature Developments |  | Venkat
US16 | User Chat History | Vikas | Venkat
US17 | Integration of tracker_stores with Mongo |  |  |  | In-Progress
US18 | User Chat History stats with Visulization | Vikas
US19 | Train the data based on user feedback - Approach | Srilekha | Venkat | bar: 2019-04-29
US20 | Recycle Unanswered question into train model (Based on fallback intents) | Vikas | bar: 2019-04-29
US21 | Context to rememmber Claim, PA and Member Eligiblity | Srilekha | Venkat
US22 | Git Respoitory | Venkat | Venkat
US23 | Fall Back Intent Development | Vikas
US24 | Debug Framework | Vikas | bar: 2019-04-29
US25 | Member Eligiblity Workflow |  | Venkat
US26 | NLP Development - Member Eligiblity | Srilekha | Venkat | bar: 2019-04-29
US27 | Accuracy - Member Eligiblity | Srilekha | Venkat | bar: 2019-04-29
US28 | Integration of intents with MongoDb | Vikas | Venkat | bar: 2019-04-29
US29 | Integration of Auto suggestions | Vikas | Venkat | bar: 2019-04-29
US30 | Digital Workflow |  | Venkat
US31 | NLP Development - Digital | Vikas | Venkat | bar: 2019-04-29
US32 | Accuracy - Digital | Vikas | Venkat | bar: 2019-04-29
US33 | Integration of intents with MongoDb | Vikas | Venkat | bar: 2019-04-29
US34 | Integration of Auto suggestions | Vikas | Venkat | bar: 2019-04-29
US35 | UI
US36 | Design About Us Page | Praveen/Prashit | Praveen | bar: 2019-04-15
US37 | Remove 'Search Dashboard Page' | Praveen/Prashit | Praveen | bar: 2019-04-15
US38 | Update FAQ's Page | Praveen/Prashit | Praveen | bar: 2019-04-15
US39 | Update Features Page | Praveen/Prashit | Praveen | bar: 2019-04-15
US40 | UI Formattings based on MOM | Praveen/Prashit | Praveen | bar: 2019-04-15
US41 | Changes to Metrics for the Overview Page | Praveen/Prashit | Praveen | bar: 2019-04-15
US42 | Integrate short questions same format of Dream11 App | Praveen/Prashit | Praveen
US43 | Multi Select Option for Providers | Praveen/Prashit | Praveen
US44 | Integration of Bot with NLP | Praveen/Prashit | Praveen
US45 | Integrate Auto-Suggestions in Chat Window | Praveen/Prashit | Praveen
US46 | Develop Metrics views for Claims Tab | Praveen/Prashit | Praveen | bar: 2019-04-29
US47 | Develop Metrics views for Prior Auth Tab - Static (Will convert to Dynamic once after acquire the data) | Praveen/Prashit | Praveen | bar: 2019-04-29
US48 | Develop Metrics views for Eligiblity Tab - Static (Will convert to Dynamic once after acquire the data) | Praveen/Prashit | Praveen | bar: 2019-04-29
US49 | Develop Metrics views for Digital Tab - Static (Will convert to Dynamic once after acquire the data) | Praveen/Prashit | Praveen | bar: 2019-04-29
US50 | Integration of showing chat history | Praveen/Prashit | Praveen | bar: 2019-04-29
US51 | Integration of Favourates | Praveen/Prashit | Praveen | bar: 2019-04-29
US52 | Email Reply functionality | Praveen/Prashit | Praveen | bar: 2019-04-29
US53 | Create MobtoDB Models for the Prior Auth, Member Eligiblity and Digital | Praveen/Prashit | Praveen | bar: 2019-04-29 to 2019-05-06
US54 | User History Integration | Praveen/Prashit | Praveen
US55 | Cross Browser Platform Support
US56 | Data
US57 | Create ER Diagram | Krishna | Krishna
US58 | Acquire data for Prior Auth | Krishna | Krishna
US59 | Acquire data for Member Eligiblity | Krishna | Krishna | bar: 2019-04-29 to 2019-05-06
US60 | Acquire data for Digital | Krishna | Krishna | bar: 2019-04-29 to 2019-05-06
US61 | BA
US62 | Provide Updated Metrcis for Overview | Arpit | Arpit |  | Done | bar: 2019-04-15
US63 | Define Claims Metrics | Arpit | Arpit |  | Done
US64 | Define Prior Auth Metrics | Arpit | Arpit
US65 | Define Eligiblity Metrics | Arpit | Arpit
US66 | Define Digital Metrics | Arpit | Arpit
US67 | NLP Worklows for Member Eligiblity | Arpit | Arpit
US68 | NLP Worklows for Digital | Arpit | Arpit
US69 | Answer Ad-hoc queries by NLP | Arpit | Arpit
US70 | Prepare short questions for Dream11 App kind of look and feel | Arpit | Arpit