## export
Formatted ID | Name | Owner | Project | Priority | State | Schedule State | Delivery date
US1989932 | Create new overview page | Balaji Bobbiganipalli | design Runway | High Attention | Open |  | 2019-08-16 22:00
DE248799 | Missing Horizontal bar chart on Payment Page for Claims Paid Breakdown | Balaji Bobbiganipalli | Design Runway | High Attention | Open | Defined | 2019-08-16 13:00
DE256103 | IE - Payments - Claims Payment Breakdown - Doesn't show Graph bars | Inder | Design Runway | High Attention | Open | Grooming | 2019-08-16 13:00
DE256105 | IE - Claims Non Payments - Trend line is not visible | Inder | Team 2 | High Attention | Open | Grooming | 2019-08-16 13:00
DE256061 | Correct spelling of ""Calculation"" in KC from ""Caluclation"" | Balaji Bobbiganipalli | Design Runway | Low | Open | Grooming | 2019-08-15 17:00
DE252011 | Security: Session not destroyed on server upon logout | Balaji Bobbiganipalli | Design Runway | Normal | Open | Defined
DE252551 | Page title and breadcrumb inconsistencies | Thota Madhukar | Team 4 | Low | Open | Defined
DE252586 | Auto-complete text bolding | Sri | Team 2 | Low | Open | Grooming
DE253347 | Incorrect Icon alignment in error messaging | Inder | Team 3 | Low | Open | Grooming
DE253469 | Select new provider/Apply filter, The page is making a lot of service calls. | Ranjith kumar Ankam | Team 1 | Low | Open | Grooming
DE256102 | On Refresh, the Provider Name goes away for a while | Sparsh | Team 2 | Low | Open | Grooming
DE250380 | Session timeout not working on UI | Balaji Bobbiganipalli | Design Runway | Normal | Open | In-Progress
DE248956 | After login and selection of provider from search window page taking more then 2 to 3 sec to redirect to overview | Thota Madhukar | Team 4 | High Attention | Ready | Accepted
DE252509 | Inconsistent TIN Filter functionality between Internal and External prod UHCInsights | Mounika Garrepalli | Team 4 | Normal | Ready | Accepted
DE252611 | Weird scroll bar next to filter button | Ranjith kumar Ankam | Team 1 | Normal | Ready | Accepted
DE252959 | Help Icons do not work when any card returns the ""No Data Available"" message | Balaji Bobbiganipalli | Design Runway | Normal | Ready | Accepted
DE253349 | Incorrect font-weight in bar graph | Balaji Bobbiganipalli | Design Runway | Normal | Ready | Accepted
DE253354 | No-bg-needed in field | Balaji Bobbiganipalli | Design Runway | Normal | Ready | Accepted
DE253355 | Incorrect styling of PA Reason tooltip | Balaji Bobbiganipalli | Design Runway | Normal | Ready | Accepted
DE253356 | Add word ""Medical"" to donut legend in PI | Balaji Bobbiganipalli | Design Runway | Normal | Ready | Accepted
DE253370 | Tin-weight styling in Tax ID select menu | Balaji Bobbiganipalli | Design Runway | Normal | Ready | Accepted
DE253371 | Use dollar sign in tooltip or whenever using dollar values in UI | Balaji Bobbiganipalli | Design Runway | Normal | Ready | Accepted
DE252582 | Active text field label positioning | Balaji Bobbiganipalli | Design Runway | Normal | Ready | Completed
DE252588 | Vertically center footer time period label on cards (global) | Balaji Bobbiganipalli | Design Runway | Normal | Ready | Completed
DE252962 | Prior Auth page data and UI loss when clicking ""Reset"" in Filters Menu | Balaji Bobbiganipalli | Team 2 | Normal | Ready | Completed
DE253346 | HCO all caps in Tin filter | Balaji Bobbiganipalli | Design Runway | Normal | Ready | Completed
DE248840 | Signout is not working as expected | Beth A Clapper | Design Runway | Normal | Ready | Completed
DE256106 | Inconsistent experience for Business GLossary across browsers and OS |  | UHC Insights | High Attention | Open | Completed
DE256109 | Internal. Search Provider text getting cut off |  | UHC Insights | Normal | Ready | Completed
DE253357 | More user affordance when closing Change Provider modal | Balaji Bobbiganipalli | Design Runway | Normal | Ready | Converted
DE253353 | Incorrect overlay color | Sri | Team 2 | Low | Open | Converted | 2019-08-16 22:00